Statement of Work (SOW)

The Early Childhood partnership of adams county (ecpac)

8859 fox drive, suite 205

thornton, co 80260

Year 5 (10/22-9/23)

# The Statement of Work (SOW) is a document which describes the scope of work required to complete a specific project.  It is a formal document and must be agreed upon by all parties involved and ultimately becomes a part of the executed agreement (Contract, PO, etc.).  In order to be effective, the SOW must contain an appropriate level of detail so all parties clearly understand what work is required, the duration of the work involved, what the deliverables are, and what is acceptable.

# Introduction/Background

Since its founding in 2004, the Early Childhood Partnership of Adams County (ECPAC) has worked to build an impressive network of partners into a strong, coordinated early childhood system serving Adams County.  ECPAC is one of 34 “Councils'' created through legislation in 2007, to improve and sustain the capacity, accessibility, quality, and affordability of early childhood services in the areas of Early Learning, Health, Social-Emotional-Mental Health, and Family Support and Parent Education.  Over the past 14 years, ECPAC has developed an effective, independent organization that nurtures and maintains a network of partners, leads collective direction-setting and strategic planning efforts, and secures the partner and financial resources needed to take action on shared outcomes.  ECPAC’s task is to convene local decision-makers, stakeholders and citizens to maximize the positive impact of systems that serve young children and families during the critical early childhood years, thereby increasing child school readiness, well-being and success. Because Adams County has one of the highest percentage of children under age 5 in Colorado and has consistently ranked in the bottom 5 of 25 rated counties for overall child well-being (Kids Count), partners are very committed to our mission to build a community where every young child and their family can reach their full potential.

ECPAC serves a variety of early childhood stakeholders in Adams County to strategically improve the capacity to increase access for families of young children to affordable and quality services and supports. ECPAC partners include over 215 individuals from over 77 organizations, elected officials, community members, and 9 family partners. The agency partners include the five local school districts, early care and education providers, early intervention services, the health department and 5 major health clinics, the mental health center, and agencies providing family support and resources, including six home visitation programs. The ECPAC Executive Director and Staff serve on a wide variety of community and state level committees and advisory councils to increase the level of collective impact and collaboration and bring the voice regarding the needs and importance of early childhood. All of the direct services that ECPAC funds - which is provided to families through parenting classes, care navigation, family leadership opportunities, and parent education and public awareness - is provided through collaborative partnerships with community organizations. ECPAC believes strongly in embedding all work into the community and always keeping focus on shared accountability for quality and outcomes.

The Child Maltreatment Prevention effort first began for ECPAC in 2014, when the Strengthening Families Framework was adopted and later written into ECPAC’s 2015-2020 Strategic Plan. The CBCAP work plan strategies are embedded into ECPAC’s new 2020-2023 Strategic Plan. Due to Adams County consistently not meeting state averages - ECPAC focuses on 4 primary population level indicators – which include 1) Child Poverty rates; 2) Child Abuse and Neglect rates; 3) Children born to mothers with 3 or more risk factors ~ primarily teens; and 4) Poor Child School outcomes ~ primarily kindergarten readiness and 3rd/4th grade reading scores. This long-standing commitment set ECPAC up to engage community partners in the 9-month Child Maltreatment Prevention planning effort through Early Milestones Colorado. This planning grant, along with the technical assistance provided, allowed ECPAC to have needed dedicated effort to move this work forward in a more intentional and deeper manner.

# Scope of Work

ECPAC expects to increase the level of support provided for families, especially those of young children and those most at-risk due to poverty, teen parenting, or other toxic stress exposure, towards the reduction of child abuse and neglect. ECPAC plans to align and embed the work plan activities with other early childhood and family initiatives in Adams County towards maximized impact, specifically including the Adams County Human Services Department (including efforts to implement Families First), and Tri-County Health Department’s Mother and Child Health Unit. This approach builds off of ECPAC’s previous efforts such as Project LAUNCH (primarily early childhood social-emotional/mental health), shared messaging, family leadership, improved policies, shifts towards two-generation work, equity, Maternal Infant Early Childhood Home Visitation, and the Collaborative for Healthy Adams County project – a shared two-generation services model. ECPAC accomplishes all of its work through partnerships with community organizations, family partners, and other key stakeholder and will use this same approach in accomplishing the outcomes presented in the Community Based Child Abuse Prevention Work Plan. This will include seeking and leveraging additional public and private funding to fully support the outcome of this work.

# Period of Performance

ECPAC began to monitor child abuse and neglect rates and consider how to use prevention strategies, in alignment with the Strengthening Families Framework in 2014. It is recognized that change in population-level outcomes, which is ultimately what ECPAC strives to achieve, takes time; this work does not have an end-date, but continues to evolve over time. However, for the purposes of this Statement of Work, the proposed strategies and activities in the Work Plan are for the time period of October 1, 2022– September 30, 2023.

# Work Plan for year 5:

| Community Based Child Abuse Prevention Work Plan |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| OUTCOMES, BENCHMARKS, AND MILESTONES |  |  |  |  |  |  |
| Outcome statement: | Full Project Outcome: As a result of the provider professional development, improvements in policies, change in social norms and integration of multiple services in a shared model in various locations in Adams County, there will be an increase in access and utilization of local resources and services so that families will be better supported by their community and more knowledgeable regarding child development and parenting, and as a result, there will be a decreased incidence of child maltreatment and families will report and increase in family protective factors. - Milestones in meeting this outcome are noted below under Schedule/Milestones |  |  |  |  |  |
| Key Activity A: Provide training to service providers and families to adequately strengthen families using best practices by 2023 (and beyond) through increased knowledge, skills, and change in practice CHANNELS FOR CHANGE: “Organizational and Practice Change” |  |  |  |  |  |  |
| Tasks |  | Time Period | Deliverable | Measurement | Person(s) Responsible | Budget Category |
| Provide training to families on the Strengthening Families 5 Protective Factors to both improve family functioning and to support family members in providing input and guidance into ongoing planning and efforts |  | October 2022-September 2023 | At least 1 training is provided to families (at least 10 families total) | # of training opportunities # of attendees (duplicated and unduplicated) Evaluation of training – increased knowledge, skills, and anticipated impact # of families engaged in additional provision of input and guidance and level of engagement | ECPAC Director of Child & Family Health and Well-being; Family Support Specialists | Personnel Supplies and Operating Training and Technical Assistance Personnel (evaluation) |
| Provide training to organizational partners on the Strengthening Families 5 Protective Factors; provide training focused on ways of supporting those impacted by substance use and reducing stigma related to SUD |  | October 2022-September 2023 | At least 3 trainings will be provided to cross-domain community service providers with a total of least 50 attendees from 12 organizations | # of training opportunities # of attendees (duplicated and unduplicated) and per domain and organization Evaluation of training – increased knowledge, skills, and anticipated impact | ECPAC Director of Child & Family Health and Well-being; Family Support Specialists | Personnel Training and Technical Assistance Travel |
| Evaluate effort |  | August- September 2023 | Collect and enter data into state data system on Activity A and related tasks | Above mentioned measurements will be entered | ECPAC Director of Child & Family Health and Well-being | Personnel |
| Key Activity B: Support the community in using inclusive, non-threatening, non-stigmatizing, culturally responsive, and welcoming messages (social norming) with families that normalize accessing services or receiving help. increase sense of community, and promote responsive caregiving as well as the Strengthening Families Protective Factors. CHANNEL FOR CHANGE: “Agency Collaboration and Community Capacity Building” |  |  |  |  |  |  |
| Tasks |  | Time Period | Deliverable | Measurement | Person(s) Responsible | Budget Category |
| Implement recommendations from national research and from state and local projects - including the Colorado Partnership for Thriving Families (CPTF) to inform communication strategies towards shifting social norms |  | October 2022-September 2023 | Attend CPTF meetings Report of recommendations followed, activities/outputs, and progress to date on the following norms: - Thriving communities and shared responsibility - Help seeking for formal and informal supports - Responsive caregiving - Strengthening Families Protective Factors | # of partner organizations engaged in social norming efforts Implementation and resulting outputs/outcomes tracking | ECPAC Executive Director, Director of Child and Family Health and Well-being, Family Support Specialists, with ECPAC Board and Partners | Personnel Travel |
| Promote developed and identified messages |  | October 2022-September 2023 | # of strategies used to promote # reached | Strategies implemented are noted # family and community partners using strategies # of families reached Outcomes of strategies | ECPAC staff, ECPAC partners, family partners | Contractors Personnel Supplies and Operating Travel |
| In partnership with organizational and family partners, host Neighborhood Events to increase social connections and provide items that promote the Strengthening Families Protective Factors |  | October 2022-September 2023 | At least 2 neighborhood events held with 25 families each | # of families reached # and type of support items distributed | ECPAC staff | Personnel Supplies and Operating Travel |
| Evaluate effort |  | August -September 2023 | Collect and enter data into state data system on Activity B and related tasks | Above mentioned measurements will be entered | ECPAC Director of Child & Family Health and Well-being | Personnel |
| Key Activity C: Ensure supportive policies (institutional, city, county, state) towards increased access and utilization of services and supports and responsive caregiving. CHANNEL FOR CHANGE: “Policy Reforms” |  |  |  |  |  |  |
| Tasks |  | Time Period | Deliverable | Measurement | Person(s) Responsible | Budget Category |
| Support and align efforts with the Colorado Partnership for Thriving Families (CPTF) and other state and local collaboratives |  | October 2022-September 2023 | Attend CPTF meetings Facilitate local discussions with community partners (Human Services and Health) towards a shared plan to prevent child abuse and neglect | Alignment of local efforts with state efforts is clear. Plan is developed with strategies, success indicators, and initial steps towards implementation | ECPAC Executive Director Director of Child and Family Health and Well-being | Personnel Travel |
| Continue to embed the Child Maltreatment Prevention lens into ECPAC’s Policy Agenda |  | October 2022-September 2023 | Clear alignment of Child Maltreatment Prevention efforts in final policy recommendations and next steps | Implementation and resulting outcomes tracking # of policy changes or enhancements made related to CM prevention | ECPAC Executive Director with ECPAC Board and Partners | Personnel |
| Use materials and presentations to educate funders and policy makers on policies and best practices for prevention of child maltreatment |  | October 2022-September 2023 | Results of use of materials/presentations on additional or leveraged funding or policy changes as related to Activity B plans | # of organizations who receive materials / presentation as related to Activity B plans Implementation and resulting outcomes tracking | ECPAC Executive Director | Personnel |
| Evaluate effort |  | August -September 2023 | Collect and enter data into state data system on Activity C and related tasks | Above mentioned measurements will be entered | ECPAC Executive Director | Personnel |
| Key Activity D: Work with community partners (organizational and families) to offer parenting/family supports and services in a more integrated way through a family resource hub model with existing and new services towards increased access and utilization and to fill identified gaps. CHANNELS FOR CHANGE: “Agency Collaboration and Community Capacity Building” towards “Individualized Services” |  |  |  |  |  |  |
| Tasks |  | Time Period | Deliverable | Measurement | Person(s) Responsible | Budget Category |
| Continue to provide opportunities for family engagement/leadership to ensure that Family Resource Center Hubs are informed by the specific community near the identified service location(s) |  | October 2022-September 2023 | Community specific needs are identified and reported with clear plans for addressing needs and barriers, as well as building upon specific community strengths | Focus groups and survey evaluations/reports | ECPAC Executive Director, Director of Child and Family Health and Well-being, Family Support Specialists, and community partners | Contractors Personnel Supplies and Operating |
| Build new, or strengthen existing, partnerships with critical and missing partners including those that address needs identified through family engagement and leadership opportunities |  | October 2022-September 2023 | New partners are noted as well as levels of engagement are tracked | ECPAC staff tracking | ECPAC Executive Director and Director of Child & Family Health and Well-being | Personnel Travel |
| Solidify partnerships with those interested in participating in the Family Resource Center Hub model by co-locating family supports into existing service delivery continuum; Support coordination of service delivery and/or the provision of appropriate referrals at FRCH and to other community services and supports |  | October 2022-September 2023 | At least two MOUs are secured for services to be delivered at one of the Hubs as additional funding allows | ECPAC staff tracking | ECPAC Executive Director and Director of Child & Family Health and Well-being with Partners | Personnel Travel Contractors |
| Coordinate efforts related to FSPP and other grant opportunities towards longer term sustainability |  | October 2022-September 2023 | Plans are well aligned 1-2 additional funding sources are secured | ECPAC staff tracking | ECPAC Executive Director and Director of Child & Family Health and Well-being with Partners | Personnel Travel |
| Evaluate effort |  | August -September 2023 | Collect and enter data into state data system on Activity D and related tasks | Above mentioned measurements will be entered | ECPAC Executive Director and Director of Child & Family Health and Well-being | Personnel |
| Key Activity E: Community members have increased awareness of child abuse prevention strategies |  |  |  |  |  |  |
| Tasks |  | Time Period | Deliverable | Measurement | Person(s) Responsible | Budget Category |
| Plan and engage in activities for Child Abuse Prevention (CAP) Month |  | February-April 2023 | CAP Month activities are completed | Activities are documented and shared; Number of participants in activities | ECPAC Director of Child & Family Health and Well-being | Salary, Supplies and Operating Costs, Travel |
| Evaluate effort |  | August -September 2023 | Collect and enter data into state data system on Activity E and related tasks | Above mentioned measurements will be entered | ECPAC Director of Child & Family Health and Well-being | Personnel |

# Schedule/Milestones – for Year 5:

| Work Plan Activity/Deliverable | Schedule | Milestone/Outcome |
| --- | --- | --- |
| Provide training and/or technical assistance to community organizations. | Full 12 months | ECPAC will provide training to at least 50 service providers from 12 community organizations by September 30, 2023. |
| Provide training to families. | Q1 and/or 3 | ECPAC Family Support Specialists will provide trainings to at least 10 families by September 30, 2023. |
| Identify and test messages and strategies to enhance sense of community and safety in seeking support. | Full 12 months | Messages are promoted through 4 social media platforms, ECPAC’s newsletters, and materials. Additional distribution mechanisms identified and continuous quality improvement on strategies implemented. |
| Ensure effective policies related to child maltreatment prevention. | Full 12 months | Demonstration of policy changes or enhancements are aligned with child maltreatment prevention outcomes in at least 1 of the 4 ECPAC priority areas. Community prevention plan is developed by September 2023. |
| Further identify specific community needs, barriers, and strengths with clear plan for partners to engage in the family resource hub model. | Full 12 months | Community input is received (through surveys, focus groups, and review of existing assessments) to further enhance implementation of Family Resource Center Hubs. |
| Plan and engage in activities for Child Abuse Prevention (CAP) Month | March - April 2023 | Engage at least 4 partners to support 2 community events to promote CAP month; Promote through 4 social media platforms and ECPAC newsletter; Recognize proclamations from municipalities. |
| Activities as determined by partners are sustained | Feb – Sept 2023 | At least 1-2 additional funding sources are secured to continue work and/or work is embedded into other current funding |
| Complete annual report | Full 12 months | CBCAP state lead will use annual report for learning to help inform TA opportunities with grantees and to collect qualitative data. |

Acceptance Criteria

The ECPAC Executive Director is responsible for ensuring all deliverables are on-track and met and will submit an annual report to the CBCAP Program Manager, including a written summary of program accomplishments and barriers to program implementation in a format provided by the CBCAP Program Manager. The Director of Child & Family Health and Well-being is responsible for regular monitoring of the CBCAP grant deliverables and will provide at least quarterly updates to the ECPAC Executive Director.  The Child Maltreatment Prevention Action Team will receive updates at least quarterly and the ECPAC Advisory Council and Board will receive updates as needed - at least bi-annually.

The acceptance of all deliverables shall reside with the Department of Early Childhood (CDEC). The designated program manager shall monitor all deliverables in order to ensure the completeness of each stage of the project and that the scope of work has been met.  The CDEC program manager shall either sign off on the approval, or reply to the vendor, in writing, advising what tasks must still be accomplished.